## Gantt Plan
Advanced Embedded Systems Lab Project – Detailed Gantt Plan
Advanced Embedded Systems Lab execution through traceable requirements, robust firmware architecture, disciplined verification, and evidence-based documentation.
WBS | Phase | Task | Assigned To | Email | Progress | Start | End | Duration | Status | Priority | Quality Evidence / Notes | time axis 2026-05-05 to 2026-06-18
1-01 | Initiation & Requirements | Analyze lab manual, assessment rubric, and 1.0 success criteria | Riwaj Ghimire | riwaj.ghimire@stud.hshl.de | 70% | 2026-05-05 | 2026-05-07 | 3 | In Progress | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
1-02 | Initiation & Requirements | Derive functional requirements and measurable acceptance criteria | Stephen Uzochi Obuh | stephen-uzochi.obuh@stud.hshl.de | 60% | 2026-05-06 | 2026-05-09 | 4 | In Progress | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-09; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
1-03 | Initiation & Requirements | Derive non-functional requirements: timing, robustness, power, safety | Bertrand Mungu Cho | bertrand-mungu.cho@stud.hshl.de | 55% | 2026-05-07 | 2026-05-11 | 5 | In Progress | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
1-04 | Initiation & Requirements | Identify target MCU, sensor/actuator interfaces, and resource limits | Daniel Chidi Chimezie | daniel-chidi.chimezie@stud.hshl.de | 50% | 2026-05-08 | 2026-05-13 | 6 | Not Started | Medium | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
1-05 | Initiation & Requirements | Create system context diagram and signal-flow overview | Riwaj Ghimire | riwaj.ghimire@stud.hshl.de | 45% | 2026-05-09 | 2026-05-11 | 3 | Not Started | Medium | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
1-06 | Initiation & Requirements | Define hardware/software boundary and module ownership | Stephen Uzochi Obuh | stephen-uzochi.obuh@stud.hshl.de | 40% | 2026-05-10 | 2026-05-13 | 4 | Not Started | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-10 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
1-07 | Initiation & Requirements | Establish Git repository, branch strategy, and issue board | Bertrand Mungu Cho | bertrand-mungu.cho@stud.hshl.de | 35% | 2026-05-11 | 2026-05-15 | 5 | Not Started | Medium | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
1-08 | Initiation & Requirements | Create documentation template for requirements-to-test traceability | Daniel Chidi Chimezie | daniel-chidi.chimezie@stud.hshl.de | 30% | 2026-05-12 | 2026-05-17 | 6 | Not Started | Medium | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
1-09 | Initiation & Requirements | Define initial bill of materials and toolchain versions | Riwaj Ghimire | riwaj.ghimire@stud.hshl.de | 25% | 2026-05-13 | 2026-05-15 | 3 | Not Started | Low | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
1-10 | Initiation & Requirements | Prepare risk register for hardware, firmware, timing, and integration | Stephen Uzochi Obuh | stephen-uzochi.obuh@stud.hshl.de | 20% | 2026-05-14 | 2026-05-17 | 4 | Not Started | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
2-01 | Architecture & Detailed Design | Design firmware architecture with layered HAL, drivers, services, and application logic | Bertrand Mungu Cho | bertrand-mungu.cho@stud.hshl.de | 70% | 2026-05-15 | 2026-05-17 | 3 | In Progress | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
2-02 | Architecture & Detailed Design | Create microcontroller pin map and alternate-function allocation | Daniel Chidi Chimezie | daniel-chidi.chimezie@stud.hshl.de | 60% | 2026-05-16 | 2026-05-19 | 4 | In Progress | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
2-03 | Architecture & Detailed Design | Design peripheral configuration plan for GPIO, ADC, PWM, UART, SPI, and I²C | Riwaj Ghimire | riwaj.ghimire@stud.hshl.de | 55% | 2026-05-17 | 2026-05-21 | 5 | In Progress | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-17 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
2-04 | Architecture & Detailed Design | Specify real-time scheduling strategy and task-period budget | Stephen Uzochi Obuh | stephen-uzochi.obuh@stud.hshl.de | 50% | 2026-05-18 | 2026-05-23 | 6 | Not Started | Medium | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-23; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
2-05 | Architecture & Detailed Design | Define interrupt architecture, priorities, and shared-resource protection | Bertrand Mungu Cho | bertrand-mungu.cho@stud.hshl.de | 45% | 2026-05-19 | 2026-05-21 | 3 | Not Started | Medium | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
2-06 | Architecture & Detailed Design | Design sensor acquisition pipeline with filtering and calibration points | Daniel Chidi Chimezie | daniel-chidi.chimezie@stud.hshl.de | 40% | 2026-05-20 | 2026-05-23 | 4 | Not Started | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-23; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
2-07 | Architecture & Detailed Design | Design actuator/control output interface and fail-safe behavior | Riwaj Ghimire | riwaj.ghimire@stud.hshl.de | 35% | 2026-05-21 | 2026-05-25 | 5 | Not Started | Medium | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
2-08 | Architecture & Detailed Design | Define communication protocol, packet format, and error handling | Stephen Uzochi Obuh | stephen-uzochi.obuh@stud.hshl.de | 30% | 2026-05-22 | 2026-05-27 | 6 | Not Started | Medium | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
2-09 | Architecture & Detailed Design | Create state-machine model for system behavior and fault modes | Bertrand Mungu Cho | bertrand-mungu.cho@stud.hshl.de | 25% | 2026-05-23 | 2026-05-25 | 3 | Not Started | Low | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
2-10 | Architecture & Detailed Design | Prepare test plan: unit tests, integration tests, HIL tests, and demo criteria | Daniel Chidi Chimezie | daniel-chidi.chimezie@stud.hshl.de | 20% | 2026-05-24 | 2026-05-27 | 4 | Not Started | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-24 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
3-01 | Implementation & Integration | Configure toolchain, compiler settings, warnings, and static-analysis rules | Riwaj Ghimire | riwaj.ghimire@stud.hshl.de | 70% | 2026-05-25 | 2026-05-27 | 3 | In Progress | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
3-02 | Implementation & Integration | Implement board support package and clock/tree initialization | Stephen Uzochi Obuh | stephen-uzochi.obuh@stud.hshl.de | 60% | 2026-05-26 | 2026-05-29 | 4 | In Progress | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
3-03 | Implementation & Integration | Implement GPIO, ADC, timer/PWM, UART, SPI, and I²C driver wrappers | Bertrand Mungu Cho | bertrand-mungu.cho@stud.hshl.de | 55% | 2026-05-27 | 2026-05-31 | 5 | In Progress | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
3-04 | Implementation & Integration | Implement sensor acquisition module with timestamped sampling | Daniel Chidi Chimezie | daniel-chidi.chimezie@stud.hshl.de | 50% | 2026-05-28 | 2026-06-02 | 6 | Not Started | Medium | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
3-05 | Implementation & Integration | Implement digital filtering, debouncing, and signal conditioning | Riwaj Ghimire | riwaj.ghimire@stud.hshl.de | 45% | 2026-05-29 | 2026-05-31 | 3 | Not Started | Medium | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
3-06 | Implementation & Integration | Implement actuator/control module with saturation and safety limits | Stephen Uzochi Obuh | stephen-uzochi.obuh@stud.hshl.de | 40% | 2026-05-30 | 2026-06-02 | 4 | Not Started | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
3-07 | Implementation & Integration | Implement application-level finite-state machine | Bertrand Mungu Cho | bertrand-mungu.cho@stud.hshl.de | 35% | 2026-05-31 | 2026-06-04 | 5 | Not Started | Medium | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-05-31 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
3-08 | Implementation & Integration | Implement communication telemetry and diagnostic logging | Daniel Chidi Chimezie | daniel-chidi.chimezie@stud.hshl.de | 30% | 2026-06-01 | 2026-06-06 | 6 | Not Started | Medium | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-06; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
3-09 | Implementation & Integration | Integrate modules using Git pull requests and code review checklist | Riwaj Ghimire | riwaj.ghimire@stud.hshl.de | 25% | 2026-06-02 | 2026-06-04 | 3 | Not Started | Low | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
3-10 | Implementation & Integration | Build first hardware-in-the-loop prototype and verify signal paths | Stephen Uzochi Obuh | stephen-uzochi.obuh@stud.hshl.de | 20% | 2026-06-03 | 2026-06-06 | 4 | Not Started | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-06; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
4-01 | Verification, Optimization & Delivery | Run unit tests for drivers, conversion routines, and state transitions | Bertrand Mungu Cho | bertrand-mungu.cho@stud.hshl.de | 70% | 2026-06-04 | 2026-06-06 | 3 | In Progress | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-06; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
4-02 | Verification, Optimization & Delivery | Execute integration tests for sensor-to-control data flow | Daniel Chidi Chimezie | daniel-chidi.chimezie@stud.hshl.de | 60% | 2026-06-05 | 2026-06-08 | 4 | In Progress | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-12; 2026-06-15 to 2026-06-18
4-03 | Verification, Optimization & Delivery | Validate real-time deadlines using oscilloscope/logic-analyzer measurements | Riwaj Ghimire | riwaj.ghimire@stud.hshl.de | 55% | 2026-06-06 | 2026-06-10 | 5 | In Progress | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-12; 2026-06-15 to 2026-06-18
4-04 | Verification, Optimization & Delivery | Perform fault-injection tests: disconnected sensor, invalid packet, timeout | Stephen Uzochi Obuh | stephen-uzochi.obuh@stud.hshl.de | 50% | 2026-06-07 | 2026-06-12 | 6 | Not Started | Medium | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-07 to 2026-06-12; 2026-06-15 to 2026-06-18
4-05 | Verification, Optimization & Delivery | Measure CPU load, memory usage, stack margin, and timing jitter | Bertrand Mungu Cho | bertrand-mungu.cho@stud.hshl.de | 45% | 2026-06-08 | 2026-06-10 | 3 | Not Started | Medium | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
4-06 | Verification, Optimization & Delivery | Optimize power consumption and execution efficiency | Daniel Chidi Chimezie | daniel-chidi.chimezie@stud.hshl.de | 40% | 2026-06-09 | 2026-06-12 | 4 | Not Started | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-18
4-07 | Verification, Optimization & Delivery | Update requirements-to-test traceability matrix with evidence | Riwaj Ghimire | riwaj.ghimire@stud.hshl.de | 35% | 2026-06-10 | 2026-06-14 | 5 | Not Started | Medium | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-18
4-08 | Verification, Optimization & Delivery | Prepare final demonstration script and backup demo scenario | Stephen Uzochi Obuh | stephen-uzochi.obuh@stud.hshl.de | 30% | 2026-06-11 | 2026-06-16 | 6 | Not Started | Medium | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-18
4-09 | Verification, Optimization & Delivery | Write final lab report with architecture, results, and engineering justification | Bertrand Mungu Cho | bertrand-mungu.cho@stud.hshl.de | 25% | 2026-06-12 | 2026-06-14 | 3 | Not Started | Low | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-18
4-10 | Verification, Optimization & Delivery | Rehearse presentation and finalize submission package | Daniel Chidi Chimezie | daniel-chidi.chimezie@stud.hshl.de | 20% | 2026-06-13 | 2026-06-16 | 4 | Not Started | High | Evidence required: screenshots, measurements, commit links, or test results. | bar: 2026-05-05 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-18

## Summary
Advanced Embedded Systems Gantt Summary
Metric | Value | Assigned To | Task Count | Avg Progress
Total tasks | 40 | Riwaj Ghimire | 10 | 46%
Project start | 2026-05-05 | Stephen Uzochi Obuh | 10 | 40%
Project end | 2026-06-18 | Bertrand Mungu Cho | 10 | 46%
Average progress | 43% | Daniel Chidi Chimezie | 10 | 40%
High-priority tasks | 20
Open / not started tasks | 28

## Team
Team Members and Equal Task Distribution
Surname | First Name(s) | Email | Group | Room
Ghimire | Riwaj | riwaj.ghimire@stud.hshl.de | Group A | A6
Obuh | Stephen Uzochi | stephen-uzochi.obuh@stud.hshl.de | Group A | A6
Cho | Bertrand Mungu | bertrand-mungu.cho@stud.hshl.de | Group A | A6
Chimezie | Daniel Chidi | daniel-chidi.chimezie@stud.hshl.de | Group A | A6